## Sheet1
Task Name | Associated Team | Owner | Custom Status | Start Date | Due Date | Duration | Priority | Created By | % Completed | Completion Date | Work hours | Billing Type
Change of MW office address - Statutory | HR Team | Muhamad Hasif Daud | Done | 30-04-2025 08:00 AM | 30-04-2025 05:00 PM | 1 | High | Muhamad Hasif Daud | 100 | 30-05-2025 05:00 PM | 3.33 | None
MDEC Expats - TOE, Cancellation, Amendment | HR Team | Muhamad Hasif Daud | Open | 2025-10-07 08:00 | 31-07-2025 06:00 PM | 6.0417 | High | Muhamad Hasif Daud | 20 |  | 6.0417 | None
HR Budget | HR Team | Muhamad Hasif Daud, Dimple Latha | Open | 2025-01-08 08:00 | 29-08-2025 06:00 PM | 7.9167 | Medium | Dimple Latha | 60 |  | 15.8333 | None
Old Office Utility - Account Closing | HR Team | Muhamad Hasif Daud | Done | 2025-12-08 08:00 | 2025-05-09 18:00 | 7.1667 | High | Muhamad Hasif Daud | 100 | 2025-05-09 18:00 | 7.1667 | None
Employment Pass (Deewakshi) - Publish Vacancy & Organize Interview Sessions | HR Team | Muhamad Hasif Daud | Open | 19-08-2025 08:00 AM | 30-09-2025 06:00 PM | 11.6667 | Medium | Muhamad Hasif Daud | 50 |  | 11.6667 | None
HR Audit | HR Team | Muhamad Hasif Daud | Open | 2025-01-09 08:00 | 15-09-2025 06:00 PM | 4.1667 | Medium | Dimple Latha | 55 |  | 4.1667 | None
Employment Pass - Sanchit - First Stage approval | HR Team | Muhamad Hasif Daud | Open | 2025-02-09 08:00 | 30-09-2025 06:00 PM | 7.9167 | Medium | Muhamad Hasif Daud | 68 |  | 7.9167 | None
Employment Pass - Deewakshi (Initiating Immigration Process) | HR Team | Muhamad Hasif Daud | Done | 2025-03-09 08:00 | 15-10-2025 06:00 PM | 11.6667 | None | Muhamad Hasif Daud | 100 | 15-10-2025 06:00 PM | 11.6667 | None
Employment Pass - Ashwini (Immigration Process) | HR Team | Muhamad Hasif Daud | Open | 2025-09-10 08:00 | 31-10-2025 06:00 PM | 6.4167 | High | Muhamad Hasif Daud | 80 |  | 6.4167 | None
Immigration - Employment Pass (Ashwini) - First Stage Approval | HR Team | Muhamad Hasif Daud | Done | 2025-03-11 08:00 | 14-11-2025 06:00 PM | 3.7917 | Medium | Muhamad Hasif Daud | 100 | 14-12-2025 06:00 PM | 3.7917 | None
Immigration - Employment Pass & Dependent Pass (Shazeen) - Initiate process | HR Team | Muhamad Hasif Daud | Open | 2025-03-11 08:00 | 14-11-2025 06:00 PM | 3.7917 | High | Muhamad Hasif Daud | 60 |  | 3.7917 | None
Probation Confirmation Process | HR Team | Jeeveetha P C K, Kushpu S | In Progress | 2024-10-06 | 30-07-2024 12:00 AM | 37 | Medium | Divya Murugesan | 45 |  | 27.75 | None
IT Awarness session with Auditor | HR Team | Unassigned User | Open | 2024-01-08 | 31-08-2024 12:00 AM | 23 | None | Jeeveetha P C K | 50 |  | 8.625 | None
Policies | HR Team | Unassigned User | Open | 26-08-2024 12:00 AM | 15-10-2024 12:00 AM | 37 | Medium | Divya Murugesan | 55 |  | 13.875 | None
PMS Policy - to be written | HR Team | Divya Murugesan | In Progress | 2025-01-05 08:00 | 30-05-2025 06:00 PM | 8.2917 | High | Divya Murugesan | 68 |  | 8.2917 | None
POSH Global awareness | HR Team | Dimple Latha, Jeeveetha P C K, Yong Ching Fan | Done | 2025-01-07 08:00 | 15-07-2025 06:00 PM | 4.1667 | High | Divya Murugesan | 100 | 15-07-2025 06:00 PM | 12.5 | None
Add all the "Onboarding & Induction" process relation docs. in a folder | HR Team | Muhamad Hasif Daud, Jeeveetha P C K | Open | 21-01-2025 12:00 AM | 23-01-2025 12:00 AM | 3 | High | Divya Murugesan | 45 |  | 2.25 | None
Remote employee' contracts - review | HR Team | Sundararaman L, Meenakshi Dabral, Divya Murugesan, Franches Ramasamy | In Progress | 24-02-2025 08:00 AM | 31-03-2025 06:00 PM | 9.7917 | Medium | Divya Murugesan | 50 |  | 39.1667 | None
Get the list ready | HR Team | Unassigned User | Open | 17-03-2025 08:00 AM | 21-03-2025 06:00 PM | 1.9167 | None | Divya Murugesan | 55 |  | 1.9167 | None
Automation - Onboarding | HR Team | Kushpu S, Jeeveetha P C K, Yong Ching Fan | In Progress | 24-03-2025 08:00 AM | 2025-11-04 18:00 | 5.6667 | High | Divya Murugesan | 68 |  | 17 | None
Payroll & PF | HR Team | Unassigned User | Done | 25-03-2025 08:00 AM | 31-03-2025 06:00 PM | 1.9167 | None | Jeeveetha P C K | 100 | 31-03-2025 06:00 PM | 1.9167 | None
Insurance For India | HR Team | Unassigned User | Open | 2025-01-04 08:00 | 15-04-2025 06:00 PM | 4.1667 | None | Jeeveetha P C K | 80 |  | 4.1667 | None
Automate R&R Process- May | HR Team | Dimple Latha, Jeeveetha P C K | Open | 25-03-2025 08:00 AM | 31-05-2025 06:00 PM | 18.7917 | None | Jeeveetha P C K | 20 |  | 37.5833 | None
Japanese Pre Sales Specialist | HR Team | Jayasri Sridhar, Yong Ching Fan | ON HOLD | 14-04-2025 08:00 AM | 21-05-2025 06:00 PM | 10.5417 | None | Jayasri Sridhar | 60 |  | 21.0833 | None
Contract - Full stack Developer (2) | HR Team | Jayasri Sridhar | Open | 2025-01-09 08:00 | 15-09-2025 06:00 PM | 4.1667 | None | Kushpu S | 45 |  | 4.1667 | None
Focus Group-Remote workers | HR Team | Unassigned User | Open | 2025-07-04 08:00 | 2025-09-04 18:00 | 1.1667 | None | Meenakshi Dabral | 80 |  | 1.1667 | None
Leadership Discovery Session- May | HR Team | Meenakshi Dabral | Open | 2025-10-04 08:00 | 18-05-2025 06:00 PM | 10.5417 | None | Meenakshi Dabral | 20 |  | 10.5417 | None
To prepare Townhall PPT | HR Team | Jeeveetha P C K | Open | 2025-01-04 08:00 | 17-04-2025 06:00 PM | 4.9167 | High | Jeeveetha P C K | 60 |  | 4.9167 | None
To update Global salary Details for April | HR Team | Unassigned User | Open | 2025-01-04 08:00 | 14-04-2025 06:00 PM | 3.7917 | None | Jeeveetha P C K | 45 |  | 3.7917 | None
Talent Acquisition | HR Team | Jayasri Sridhar | Open | 17-04-2025 08:00 AM | 30-06-2025 06:00 PM | 19.9167 | None | Mahalakshmi P | 50 |  | 19.9167 | None
Rewards & Recognition - April | HR Team | Jeeveetha P C K | Open | 25-04-2025 08:00 AM | 15-05-2025 06:00 PM | 5.6667 | High | Jeeveetha P C K | 55 |  | 5.6667 | None
Employee - Stories beyond the wall - April | HR Team | Meenakshi Dabral, Jeeveetha P C K | Open | 23-04-2025 08:00 AM | 15-05-2025 06:00 PM | 6.4167 | None | Jeeveetha P C K | 68 |  | 12.8333 | None
Explore Hr AI courses | HR Team | Unassigned User | Done | 16-04-2025 08:00 AM | 30-04-2025 06:00 PM | 4.1667 | None | Jayasri Sridhar | 100 | 30-04-2025 06:00 PM | 4.1667 | None
HR Org Chart | HR Team | Jeeveetha P C K | Open | 23-04-2025 08:00 AM | 29-04-2025 06:00 PM | 1.9167 | None | Jeeveetha P C K | 45 |  | 1.9167 | None
Payroll for India - April | HR Team | Jeeveetha P C K | Open | 25-04-2025 08:00 AM | 30-04-2025 06:00 PM | 1.5417 | None | Jeeveetha P C K | 50 |  | 1.5417 | None
R & R Automation - demo call with Meenakshi | HR Team | Jeeveetha P C K | Open | 2025-01-08 08:00 | 15-08-2025 06:00 PM | 4.1667 | High | Jeeveetha P C K | 20 |  | 4.1667 | None
Zoho Expenses walkthrough - Shyam | HR Team | Jeeveetha P C K | Open | 25-04-2025 08:00 AM | 28-04-2025 06:00 PM | 0.79167 | None | Jeeveetha P C K | 60 |  | 0.79167 | None
Townhall PPT for May | HR Team | Jeeveetha P C K | Open | 25-04-2025 08:00 AM | 19-05-2025 06:00 PM | 6.4167 | None | Jeeveetha P C K | 45 |  | 6.4167 | None
Equity update - New investment | HR Team | Yong Ching Fan | ON HOLD | 2025-12-05 08:00 | 14-05-2025 06:00 PM | 1.1667 | Medium | Yong Ching Fan | 80 |  | 1.1667 | None
Flexi Benefits policy - for other (MY, India, SG, Off-shore) Markets | HR Team | Sundararaman L, Meenakshi Dabral, Dimple Latha, Divya Murugesan, Franches Ramasamy | Open | 28-04-2025 08:00 AM | 2025-02-05 18:00 | 1.9167 | High | Divya Murugesan | 20 |  | 9.5833 | None
Login Issue Discussion - Tarajyau (BGV Tool) | HR Team | Jeeveetha P C K | Open | 29-04-2025 08:00 AM | 30-04-2025 06:00 PM | 0.79167 | None | Jeeveetha P C K | 60 |  | 0.79167 | None
Approval from Sundar Sir for Insurance Payment | HR Team | Jeeveetha P C K | Open | 29-04-2025 08:00 AM | 30-04-2025 06:00 PM | 0.79167 | None | Jeeveetha P C K | 45 |  | 0.79167 | None
Zoho Expense Workflow Configuration | HR Team | Jeeveetha P C K | Open | 29-04-2025 08:00 AM | 15-05-2025 06:00 PM | 4.9167 | None | Jeeveetha P C K | 50 |  | 4.9167 | None
Work with Shazeen for the Video | HR Team | Jeeveetha P C K | Open | 29-04-2025 08:00 AM | 15-05-2025 06:00 PM | 4.9167 | None | Jeeveetha P C K | 80 |  | 4.9167 | None
Update MIS and Zoho one | HR Team | Muhamad Hasif Daud, Jeeveetha P C K | Open | 29-04-2025 02:00 PM | 30-04-2025 06:00 PM | 0.54167 | High | Kushpu S | 20 |  | 1.0833 | None
Tech Lead/ Solution Architect Position | HR Team | Kushpu S | In Progress | 2025-01-09 08:00 | 30-09-2025 06:00 PM | 8.2917 | High | Kushpu S | 60 |  | 8.2917 | None
Zoho Payroll Discussion with Zoho Team | HR Team | Dimple Latha, Jeeveetha P C K | Open | 16-07-2025 08:00 AM | 31-07-2025 06:00 PM | 4.5417 | None | Jeeveetha P C K | 45 |  | 9.0833 | None
Q1 Salary report | HR Team | Jeeveetha P C K | Open | 2025-12-05 08:00 | 15-05-2025 06:00 PM | 1.5417 | None | Jeeveetha P C K | 50 |  | 1.5417 | None
Flexi Benefit letter - India | HR Team | Jeeveetha P C K | Open | 13-05-2025 08:00 AM | 15-05-2025 06:00 PM | 1.1667 | None | Jeeveetha P C K | 55 |  | 1.1667 | None
Office - Business Open Day | HR Team | Muhamad Hasif Daud | Open | 16-05-2025 08:00 AM | 21-05-2025 06:00 PM | 1.5417 | Medium | Muhamad Hasif Daud | 68 |  | 1.5417 | None
Generate report - Goal setting for Q2 | HR Team | Kushpu S, Jeeveetha P C K | Done | 28-05-2025 08:00 AM | 30-05-2025 06:00 PM | 1.1667 | None | Kushpu S | 100 | 30-05-2025 06:00 PM | 2.3333 | None
Aruna kumar - Final Call | HR Team | Kushpu S | Open | 20-05-2025 08:00 AM | 20-05-2025 06:00 PM | 0.41667 | None | Kushpu S | 45 |  | 0.41667 | None
Attendance Check | HR Team | Kushpu S, Jeeveetha P C K | Open | 27-05-2025 08:00 AM | 30-05-2025 06:00 PM | 1.5417 | None | Kushpu S | 50 |  | 3.0833 | None
Syaril's Review | HR Team | Kushpu S | Open | 20-05-2025 08:00 AM | 20-05-2025 06:00 PM | 0.41667 | None | Kushpu S | 20 |  | 0.41667 | None
Contract Renewal/ Non renewal | HR Team | Unassigned User | Open | 26-04-2025 08:00 AM | 30-05-2025 06:00 PM | 9.7917 | Medium | Divya Murugesan | 60 |  | 9.7917 | None
Townhall - June | HR Team | Jeeveetha P C K | Open | 2025-01-06 08:00 | 15-06-2025 06:00 PM | 4.5417 | High | Jeeveetha P C K | 45 |  | 4.5417 | None
Stories beyond the wall - June | HR Team | Jeeveetha P C K | Open | 23-05-2025 08:00 AM | 31-05-2025 06:00 PM | 2.6667 | High | Jeeveetha P C K | 80 |  | 2.6667 | None
Rewards & Recognition | HR Team | Jeeveetha P C K | Open | 23-05-2025 08:00 AM | 31-05-2025 06:00 PM | 2.6667 | High | Jeeveetha P C K | 20 |  | 2.6667 | None
Business Updates - May | HR Team | Jeeveetha P C K | Open | 23-05-2025 08:00 AM | 31-05-2025 06:00 PM | 2.6667 | High | Jeeveetha P C K | 45 |  | 2.6667 | None
HR Slides for Towhall | HR Team | Jeeveetha P C K | Open | 26-05-2025 08:00 AM | 31-05-2025 06:00 PM | 2.2917 | None | Jeeveetha P C K | 80 |  | 2.2917 | None
AI Policy - Review with Meenakshi | HR Team | Dimple Latha, Jeeveetha P C K | Open | 2025-01-08 08:00 | 15-08-2025 06:00 PM | 4.1667 | High | Jeeveetha P C K | 20 |  | 8.3333 | None
Increment & Flexi benefit letters for revised numbers - India | HR Team | Jeeveetha P C K | Open | 19-05-2025 08:00 AM | 23-05-2025 06:00 PM | 1.9167 | None | Jeeveetha P C K | 60 |  | 1.9167 | None
ID Card - To send the Required Details to the Vendor | HR Team | Jeeveetha P C K | Open | 16-07-2025 08:00 AM | 31-07-2025 06:00 PM | 4.5417 | None | Jeeveetha P C K | 45 |  | 4.5417 | None
Payroll - May ( India ) | HR Team | Jeeveetha P C K | Open | 2025-02-06 08:00 | 13-06-2025 06:00 PM | 3.7917 | None | Jeeveetha P C K | 50 |  | 3.7917 | None
MY & SG Payroll Processing | HR Team | Muhamad Hasif Daud | Open | 22-05-2025 08:00 AM | 28-05-2025 06:00 PM | 1.9167 | High | Muhamad Hasif Daud | 80 |  | 1.9167 | None
MDEC - IMMIGRATION : Employment Pass (Renewal) - Gopi Selvam | HR Team | Muhamad Hasif Daud | Open | 22-05-2025 08:00 AM | 22-05-2025 05:00 PM | 1 | Medium | Muhamad Hasif Daud | 20 |  | 0.375 | None
90th day Review - Manoj | HR Team | Kushpu S | Open | 22-05-2025 08:00 AM | 22-05-2025 06:00 PM | 0.41667 | None | Kushpu S | 60 |  | 0.41667 | None
Learning Library update | HR Team | Kushpu S | Open | 23-05-2025 08:00 AM | 28-05-2025 06:00 PM | 1.5417 | None | Kushpu S | 45 |  | 1.5417 | None
Pre-sales & Marketing Position (Dubai) | HR Team | Yong Ching Fan | Open | 23-06-2025 08:00 AM | 2025-11-07 18:00 | 5.6667 | None | Yong Ching Fan | 50 |  | 5.6667 | None
Zoho Learn - POD Course Upload | HR Team | Kushpu S | Open | 23-05-2025 08:00 AM | 27-05-2025 06:00 PM | 1.1667 | None | Kushpu S | 55 |  | 1.1667 | None
Equity Update | HR Team | Yong Ching Fan | ON HOLD | 26-05-2025 08:00 AM | 2025-06-06 18:00 | 3.7917 | None | Yong Ching Fan | 68 |  | 3.7917 | None
Comp & Ben Framework - Market Analysis | HR Team | Dimple Latha, Jeeveetha P C K | Done | 16-06-2025 08:00 AM | 30-06-2025 06:00 PM | 4.1667 | High | Jeeveetha P C K | 100 | 30-06-2025 06:00 PM | 8.3333 | None
Niranjan Exit Discussion | HR Team | Kushpu S, Pramode Divakaran, Vanaraj C | Open | 2025-03-06 08:00 | 2025-03-06 18:00 | 0.41667 | High | Kushpu S | 45 |  | 1.25 | None
Exit Analysis Report | HR Team | Kushpu S | Open | 2025-03-06 08:00 | 2025-06-06 18:00 | 1.5417 | High | Kushpu S | 80 |  | 1.5417 | None
Key TALENT & Retention - Data Report | HR Team | Kushpu S | Open | 2025-11-06 08:00 | 20-06-2025 06:00 PM | 3.0417 | High | Kushpu S | 20 |  | 3.0417 | None
Discussion with Shyam - Skill Matrix and Talent Alignment | HR Team | Shyam Krishnamurthy, Kushpu S, Dimple Latha | Open | 2025-06-06 08:00 | 2025-11-06 18:00 | 1.5417 | High | Kushpu S | 60 |  | 4.625 | None
ESOP Policy | HR Team | Yong Ching Fan | Open | 2025-01-07 08:00 | 15-07-2025 06:00 PM | 4.1667 | Medium | Yong Ching Fan | 45 |  | 4.1667 | None
Saravana kumar - Exit process | HR Team | Kushpu S | Open | 2025-05-06 08:00 | 2025-06-06 18:00 | 0.79167 | None | Kushpu S | 50 |  | 0.79167 | None
GMC Insurance Training by the Vendor | HR Team | Dimple Latha, Jeeveetha P C K | Open | 2025-05-08 08:00 | 2025-07-08 18:00 | 1.1667 | None | Jeeveetha P C K | 80 |  | 2.3333 | None
Issuing E Card | HR Team | Jeeveetha P C K | Open | 2025-02-06 08:00 | 15-06-2025 06:00 PM | 4.1667 | None | Jeeveetha P C K | 20 |  | 4.1667 | None
HR Manager Position in KL | HR Team | Yong Ching Fan | Open | 23-06-2025 08:00 AM | 2025-11-07 18:00 | 5.6667 | High | Yong Ching Fan | 60 |  | 5.6667 | None
Probation Review Email Trigger | HR Team | Jeeveetha P C K | Open | 2025-01-07 08:00 | 15-07-2025 06:00 PM | 4.1667 | None | Jeeveetha P C K | 45 |  | 4.1667 | None
R & R Policy | HR Team | Dimple Latha, Jeeveetha P C K | Open | 16-06-2025 08:00 AM | 30-06-2025 06:00 PM | 4.1667 | High | Jeeveetha P C K | 50 |  | 8.3333 | None
Survey | HR Team | Jeeveetha P C K | Open | 16-06-2025 08:00 AM | 30-06-2025 06:00 PM | 4.1667 | None | Jeeveetha P C K | 55 |  | 4.1667 | None
Escalation / Approval Matrix | HR Team | Dimple Latha, Jeeveetha P C K | Open | 16-07-2025 08:00 AM | 31-07-2025 06:00 PM | 4.5417 | None | Jeeveetha P C K | 68 |  | 9.0833 | None
NM team's Skill matrix | HR Team | Meenakshi Dabral, Kushpu S, Narayan Murthy | Done | 2025-11-06 08:00 | 20-06-2025 06:00 PM | 3.0417 | High | Kushpu S | 100 | 25-06-2025 06:00 PM | 9.125 | None
IT Asset Dashboard Update | HR Team | Vinoth Kumar, Kushpu S, Kaviyarasu S | Open | 18-06-2025 08:00 AM | 24-06-2025 06:00 PM | 1.9167 | None | Kushpu S | 45 |  | 5.75 | None
Offer Letter / Contract / Confirmation / Salary Revision | HR Team | Muhamad Hasif Daud | Open | 2025-01-07 08:00 | 31-07-2025 06:00 PM | 8.6667 | Medium | Muhamad Hasif Daud | 80 |  | 8.6667 | None
Chief of Staff Position | HR Team | Yong Ching Fan | Open | 16-07-2025 08:00 AM | 31-07-2025 06:00 PM | 4.5417 | High | Yong Ching Fan | 20 |  | 4.5417 | None
Welcoming New Joiner Deck | HR Team | Kushpu S, Jeeveetha P C K, Yong Ching Fan | Open | 2025-01-07 08:00 | 15-07-2025 06:00 PM | 4.1667 | Medium | Yong Ching Fan | 60 |  | 12.5 | None
L&D - Zoho Learn Dashboard - Monthwise Report | HR Team | Kushpu S, Bhuvaneshwaran M | Open | 16-07-2025 08:00 AM | 23-07-2025 06:00 PM | 2.2917 | None | Kushpu S | 45 |  | 4.5833 | None
Q3 - Goal Setting Email | HR Team | Kushpu S | Open | 20-06-2025 08:00 AM | 20-06-2025 06:00 PM | 0.41667 | None | Kushpu S | 50 |  | 0.41667 | None
Joshua's relocation to japan | HR Team | Muhamad Hasif Daud, Kushpu S, Dimple Latha | Open | 20-06-2025 08:00 AM | 30-06-2025 06:00 PM | 2.6667 | None | Kushpu S | 80 |  | 8 | None
MWMY, MWSG & Offshore Payroll | HR Team | Muhamad Hasif Daud | Open | 2025-01-07 08:00 | 15-07-2025 06:00 PM | 4.1667 | High | Muhamad Hasif Daud | 20 |  | 4.1667 | None
Flexi Enrollment - Indonesia (Revision) | HR Team | Muhamad Hasif Daud | Open | 2025-01-07 08:00 | 15-07-2025 06:00 PM | 4.1667 | High | Muhamad Hasif Daud | 60 |  | 4.1667 | None
Linkedin Posting - Planning & Data Lead | HR Team | Yong Ching Fan | Open | 23-06-2025 08:00 AM | 31-07-2025 06:00 PM | 10.9167 | High | Yong Ching Fan | 45 |  | 10.9167 | None
India Payroll - June | HR Team | Jeeveetha P C K | Open | 26-06-2025 08:00 AM | 30-06-2025 06:00 PM | 1.1667 | None | Jeeveetha P C K | 50 |  | 1.1667 | None
Policy - Leave (Global) | HR Team | Muhamad Hasif Daud | Open | 16-07-2025 08:00 AM | 29-08-2025 06:00 PM | 12.4167 | High | Muhamad Hasif Daud | 55 |  | 12.4167 | None
Media Planning & Data Analytics Lead (On hold) | HR Team | Yong Ching Fan | Open | 2025-01-07 08:00 | 15-07-2025 06:00 PM | 4.1667 | High | Yong Ching Fan | 68 |  | 4.1667 | None
Virtual Workshop - Remote (RISE -topic) | HR Team | Yong Ching Fan | Done | 16-07-2025 08:00 AM | 31-07-2025 06:00 PM | 4.5417 | None | Yong Ching Fan | 100 | 31-07-2025 06:00 PM | 4.5417 | None
Engagement with Monash University | HR Team | Yong Ching Fan | Open | 2025-03-07 08:00 | 15-07-2025 06:00 PM | 3.4167 | Medium | Yong Ching Fan | 80 |  | 3.4167 | None
MIS - LDSK/INSIGHTZ | HR Team | Muhamad Hasif Daud | Open | 2025-07-07 08:00 | 30-09-2025 06:00 PM | 23.2917 | Medium | Muhamad Hasif Daud | 20 |  | 23.2917 | None
Safwaan's announcement back to marketing team | HR Team | Yong Ching Fan | Open | 2025-07-07 08:00 | 2025-07-07 18:00 | 0.41667 | High | Yong Ching Fan | 60 |  | 0.41667 | None
RISE Updates (Video) for Townhall | HR Team | Yong Ching Fan | Open | 2025-07-07 08:00 | 2025-10-07 18:00 | 1.5417 | None | Yong Ching Fan | 45 |  | 1.5417 | None
Communication to Ankur & Onboarding | HR Team | Yong Ching Fan | Open | 2025-07-07 08:00 | 15-07-2025 06:00 PM | 2.6667 | High | Yong Ching Fan | 50 |  | 2.6667 | None
Leadership Orgn Chart after merging | HR Team | Yong Ching Fan | Open | 2025-01-07 08:00 | 2025-08-07 18:00 | 2.2917 | High | Yong Ching Fan | 55 |  | 2.2917 | None
Sprinto Cleanup | HR Team | Muhamad Hasif Daud, Yong Ching Fan | Open | 2025-11-07 08:00 | 2025-11-07 17:00 | 1 | Medium | Muhamad Hasif Daud | 68 |  | 0.75 | None
Adtech New Structure | HR Team | Yong Ching Fan | Done | 14-07-2025 08:00 AM | 18-07-2025 06:00 PM | 1.9167 | Medium | Yong Ching Fan | 100 | 18-07-2025 06:00 PM | 1.9167 | None
WOO Grant - Minor update | HR Team | Yong Ching Fan | Open | 14-07-2025 08:00 AM | 15-07-2025 06:00 PM | 0.79167 | High | Yong Ching Fan | 80 |  | 0.79167 | None
MW Benefit Plan Approval for July | HR Team | Dimple Latha, Jeeveetha P C K | Open | 18-07-2025 08:00 AM | 31-07-2025 06:00 PM | 3.7917 | High | Jeeveetha P C K | 20 |  | 7.5833 | None
Payroll -July | HR Team | Jeeveetha P C K | Open | 22-07-2025 08:00 AM | 31-07-2025 06:00 PM | 3.0417 | None | Jeeveetha P C K | 60 |  | 3.0417 | None
Q2 Managers Review | HR Team | Meenakshi Dabral | Open | 16-08-2025 08:00 AM | 31-08-2025 06:00 PM | 4.5417 | Medium | Dimple Latha | 45 |  | 4.5417 | None
Remote Contractor Agency | HR Team | Muhamad Hasif Daud, Dimple Latha | Open | 16-08-2025 08:00 AM | 31-08-2025 06:00 PM | 4.5417 | High | Dimple Latha | 50 |  | 9.0833 | None
HR Audit | HR Team | Meenakshi Dabral | Open | 17-07-2025 08:00 AM | 31-07-2025 06:00 PM | 4.1667 | None | Dimple Latha | 55 |  | 4.1667 | None
Onboarding Deck - Fine tuning | HR Team | Yong Ching Fan | Open | 16-07-2025 08:00 AM | 25-07-2025 06:00 PM | 3.0417 | Medium | Yong Ching Fan | 68 |  | 3.0417 | None
Call with Linkedin - for subscriptions | HR Team | Yong Ching Fan | Done | 17-07-2025 08:00 AM | 17-07-2025 06:00 PM | 0.41667 | None | Yong Ching Fan | 100 | 26-07-2025 06:00 PM | 5.45 | None
ESOP Policy Briefing to Team | HR Team | Yong Ching Fan | Open | 17-07-2025 08:00 AM | 17-07-2025 06:00 PM | 0.41667 | Medium | Yong Ching Fan | 45 |  | 0.41667 | None
Daily Sprint Call | HR Team | Yong Ching Fan | Open | 17-07-2025 08:00 AM | 31-07-2025 06:00 PM | 4.1667 | Medium | Yong Ching Fan | 50 |  | 4.1667 | None
ESOP Policy - Final Cleanup | HR Team | Yong Ching Fan | Open | 17-07-2025 08:00 AM | 31-07-2025 06:00 PM | 4.1667 | High | Yong Ching Fan | 55 |  | 4.1667 | None
Probation Confirmation Review - Niranjana | HR Team | Yong Ching Fan | Open | 21-07-2025 08:00 AM | 23-07-2025 06:00 PM | 1.1667 | Medium | Yong Ching Fan | 68 |  | 1.1667 | None
Focus Group - Meeting (Remote) | HR Team | Dimple Latha, Yong Ching Fan | Done | 21-07-2025 08:00 AM | 25-07-2025 06:00 PM | 1.9167 | High | Kushpu S | 100 | 28-07-2025 06:00 PM | 3.8333 | None
Payroll Processing | HR Team | Muhamad Hasif Daud | Open | 21-07-2025 08:00 AM | 31-07-2025 06:00 PM | 3.4167 | High | Muhamad Hasif Daud | 80 |  | 3.4167 | None
Briefing to Admin Support (part timer) | HR Team | Yong Ching Fan | Open | 22-07-2025 08:00 AM | 24-07-2025 06:00 PM | 1.1667 | High | Yong Ching Fan | 20 |  | 1.1667 | None
Appraisal Self Review Follow-up | HR Team | Yong Ching Fan | Open | 22-07-2025 08:00 AM | 24-07-2025 06:00 PM | 1.1667 | High | Yong Ching Fan | 60 |  | 1.1667 | None
Statutory Process & Payment | HR Team | Muhamad Hasif Daud | Open | 23-07-2025 08:00 AM | 31-10-2025 06:00 PM | 27.4167 | None | Muhamad Hasif Daud | 45 |  | 27.4167 | None
Hiring Playbook | HR Team | Jayasri Sridhar | Open | 2025-01-10 08:00 | 15-10-2025 06:00 PM | 4.1667 | Medium | Jayasri Sridhar | 80 |  | 4.1667 | None
Pre-sales & Marketing Support - Dubai (KIV) | HR Team | Yong Ching Fan | Open | 24-07-2025 08:00 AM | 25-07-2025 06:00 PM | 0.79167 | None | Yong Ching Fan | 20 |  | 0.79167 | None
Leadership Biodata Updates | HR Team | Yong Ching Fan | Open | 23-07-2025 08:00 AM | 25-07-2025 06:00 PM | 1.1667 | Medium | Yong Ching Fan | 60 |  | 1.1667 | None
Shyam's team - Upskilling | HR Team | Kushpu S | Open | 2025-01-08 08:00 | 15-08-2025 06:00 PM | 4.1667 | None | Kushpu S | 45 |  | 4.1667 | None
NEw joinee to join 4 Stand-up/ POD calls | HR Team | Kushpu S | Open | 2025-01-09 08:00 | 15-09-2025 06:00 PM | 4.1667 | None | Kushpu S | 50 |  | 4.1667 | None
Moving Values Sharing & Taskforce (Onsite+Remote) | HR Team | Yong Ching Fan | Open | 28-07-2025 08:00 AM | 31-07-2025 06:00 PM | 1.5417 | Medium | Yong Ching Fan | 55 |  | 1.5417 | None
Onboarding Plans & Teambuilding for Insightz Club staff | HR Team | Yong Ching Fan | Open | 29-07-2025 08:00 AM | 2025-08-08 18:00 | 3.4167 | High | Yong Ching Fan | 68 |  | 3.4167 | None
Hiring Playbook | HR Team | Jayasri Sridhar | Done | 25-07-2025 08:00 AM | 31-07-2025 06:00 PM | 1.9167 | None | Jayasri Sridhar | 100 | 31-07-2025 06:00 PM | 1.9167 | None
Onboarding - Dudu | HR Team | Yong Ching Fan | Open | 29-07-2025 08:00 AM | 29-07-2025 06:00 PM | 0.41667 | High | Yong Ching Fan | 45 |  | 0.41667 | None
Joshua's Relocation | HR Team | Yong Ching Fan | Open | 2025-01-08 08:00 | 29-08-2025 06:00 PM | 7.9167 | High | Yong Ching Fan | 50 |  | 7.9167 | None
Linkedin Alumni Page | HR Team | Yong Ching Fan | Open | 2025-01-08 08:00 | 15-08-2025 06:00 PM | 4.1667 | Medium | Yong Ching Fan | 20 |  | 4.1667 | None
Payroll Summary | HR Team | Muhamad Hasif Daud | Open | 2025-04-08 08:00 | 2025-06-08 18:00 | 1.1667 | High | Muhamad Hasif Daud | 60 |  | 1.1667 | None
Onboarding Yadhav - Customer Success | HR Team | Yong Ching Fan | Open | 2025-04-08 08:00 | 15-08-2025 06:00 PM | 3.7917 | High | Yong Ching Fan | 45 |  | 3.7917 | None
Manson's Contract to Third Party | HR Team | Yong Ching Fan | Open | 2025-04-08 08:00 | 15-08-2025 06:00 PM | 3.7917 | High | Yong Ching Fan | 80 |  | 3.7917 | None
WFH - Automation | HR Team | Muhamad Hasif Daud | Open | 2025-01-08 08:00 | 30-09-2025 06:00 PM | 16.1667 | Medium | Muhamad Hasif Daud | 20 |  | 16.1667 | None
AI Behavioural Assessment with Salman | HR Team | Jayasri Sridhar, Meenakshi Dabral | Open | 15-09-2025 08:00 AM | 30-09-2025 06:00 PM | 4.5417 | None | Jayasri Sridhar | 60 |  | 9.0833 | None
Zoho Payroll Integration For Attendance - Phase 2 | HR Team | Jeeveetha P C K | Open | 16-09-2025 08:00 AM | 30-09-2025 06:00 PM | 4.1667 | High | Jeeveetha P C K | 45 |  | 4.1667 | None
Include Insurance in Zoho Payroll | HR Team | Jeeveetha P C K | Open | 2025-08-08 08:00 | 15-08-2025 06:00 PM | 2.2917 | None | Jeeveetha P C K | 50 |  | 2.2917 | None
Letters & Documents | HR Team | Muhamad Hasif Daud | Open | 2025-06-08 08:00 | 29-08-2025 06:00 PM | 6.7917 | Medium | Muhamad Hasif Daud | 80 |  | 6.7917 | None
Tech + Product (100%), Mid-Manager Capability Program (matrix) | HR Team | Kushpu S, Dimple Latha | Open | 16-09-2025 08:00 AM | 15-10-2025 06:00 PM | 8.2917 | None | Kushpu S | 20 |  | 16.5833 | None
Rise: Upskill/Reskill : ' Agility beyond Scrum' | HR Team | Kushpu S, Dimple Latha, Mahalakshmi P | Open | 16-09-2025 08:00 AM | 30-09-2025 06:00 PM | 4.1667 | None | Kushpu S | 60 |  | 12.5 | None
VOE with action plan and closure | HR Team | Kushpu S, Dimple Latha | Open | 16-09-2025 08:00 AM | 15-10-2025 06:00 PM | 8.2917 | None | Kushpu S | 45 |  | 16.5833 | None
Key Talent engagement plan min once a month training | HR Team | Kushpu S | Open | 16-08-2025 08:00 AM | 31-08-2025 06:00 PM | 4.5417 | None | Kushpu S | 50 |  | 4.5417 | None
Deewakshi's conversion | HR Team | Yong Ching Fan | Open | 2025-06-08 08:00 | 29-08-2025 06:00 PM | 6.7917 | High | Yong Ching Fan | 55 |  | 6.7917 | None
A Day in MediaTech - Cross Function Learning | HR Team | Yong Ching Fan | Open | 2025-07-08 08:00 | 29-08-2025 06:00 PM | 6.4167 | Medium | Yong Ching Fan | 68 |  | 6.4167 | None
HR Budget | HR Team | Yong Ching Fan | Done | 2025-07-08 08:00 | 13-08-2025 06:00 PM | 1.9167 | Medium | Yong Ching Fan | 100 | 13-08-2025 06:00 PM | 1.9167 | None
Insurance Awareness Workshop (KL Office) | HR Team | Yong Ching Fan | Open | 2025-11-08 08:00 | 22-08-2025 06:00 PM | 3.7917 | None | Yong Ching Fan | 45 |  | 3.7917 | None
Employee Happiness Award | HR Team | Yong Ching Fan | Open | 14-08-2025 08:00 AM | 21-08-2025 06:00 PM | 2.2917 | Low | Yong Ching Fan | 50 |  | 2.2917 | None
Survey Analysis | HR Team | Jeeveetha P C K | Open | 18-08-2025 08:00 AM | 19-08-2025 06:00 PM | 0.79167 | High | Jeeveetha P C K | 20 |  | 0.79167 | None
Moving Values Taskforce Mtg (Welcome + Brainstorming) | HR Team | Yong Ching Fan | Open | 2025-11-08 08:00 | 15-08-2025 06:00 PM | 1.9167 | High | Yong Ching Fan | 60 |  | 1.9167 | None
Upload Moving Values on Zoho Learn | HR Team | Kushpu S | Open | 18-08-2025 08:00 AM | 29-08-2025 06:00 PM | 3.7917 | None | Kushpu S | 45 |  | 3.7917 | None
MW Benefit approval & Calculations | HR Team | Jeeveetha P C K | Open | 25-08-2025 08:00 AM | 30-08-2025 06:00 PM | 2.2917 | High | Jeeveetha P C K | 80 |  | 2.2917 | None
Payroll for August - India | HR Team | Jeeveetha P C K | Open | 21-08-2025 08:00 AM | 27-08-2025 06:00 PM | 1.9167 | High | Jeeveetha P C K | 20 |  | 1.9167 | None
Travel Policy | HR Team | Yong Ching Fan | Open | 2025-01-09 08:00 | 26-09-2025 06:00 PM | 7.5417 | Medium | Yong Ching Fan | 45 |  | 7.5417 | None
Randoph's Salary Advance | HR Team | Yong Ching Fan | Open | 18-08-2025 08:00 AM | 22-08-2025 06:00 PM | 1.9167 | High | Yong Ching Fan | 80 |  | 1.9167 | None
1: 1 Session with Samuel (new joiner ard 3 mths) | HR Team | Yong Ching Fan | Open | 19-08-2025 08:00 AM | 19-08-2025 06:00 PM | 0.41667 | Medium | Yong Ching Fan | 20 |  | 0.41667 | None
Hiring - Solution Architect / Tech Lead (KL) | HR Team | Yong Ching Fan | Open | 19-08-2025 08:00 AM | 29-08-2025 06:00 PM | 3.4167 | Medium | Yong Ching Fan | 60 |  | 3.4167 | None
Payroll Process - Global | HR Team | Muhamad Hasif Daud | Open | 21-08-2025 08:00 AM | 29-08-2025 06:00 PM | 2.6667 | High | Muhamad Hasif Daud | 45 |  | 2.6667 | None
Stand-up / POD for Newjoiners | HR Team | Yong Ching Fan | Open | 25-08-2025 08:00 AM | 2025-02-09 18:00 | 2.6667 | Medium | Yong Ching Fan | 50 |  | 2.6667 | None
Payroll Summary - Global | HR Team | Muhamad Hasif Daud | Open | 2025-02-09 08:00 | 2025-11-09 18:00 | 3.0417 | High | Muhamad Hasif Daud | 80 |  | 3.0417 | None
Insurance - Annual Renewal (MY) - Approval Stage | HR Team | Muhamad Hasif Daud | Open | 2025-02-09 08:00 | 31-10-2025 06:00 PM | 16.5417 | High | Muhamad Hasif Daud | 20 |  | 16.5417 | None
Employment Pass Renewal Process - Sanchit | HR Team | Muhamad Hasif Daud | Open | 21-08-2025 08:00 AM | 2025-05-09 18:00 | 4.5417 | High | Muhamad Hasif Daud | 60 |  | 4.5417 | None
MW Values 1st Teaser | HR Team | Yong Ching Fan | Open | 25-08-2025 08:00 AM | 29-08-2025 06:00 PM | 1.9167 | High | Yong Ching Fan | 45 |  | 1.9167 | None
MW Values - Teaser 2 | HR Team | Yong Ching Fan | Open | 27-08-2025 08:00 AM | 29-08-2025 06:00 PM | 1.1667 | High | Yong Ching Fan | 50 |  | 1.1667 | None
Townhall - September | HR Team | Jeeveetha P C K | Open | 2025-01-09 08:00 | 2025-11-09 18:00 | 3.4167 | None | Jeeveetha P C K | 55 |  | 3.4167 | None
To send the nominations for voting to all mgrs. | HR Team | Jeeveetha P C K | Open | 2025-01-09 08:00 | 2025-04-09 18:00 | 1.5417 | None | Jeeveetha P C K | 68 |  | 1.5417 | None
HR slides | HR Team | Jeeveetha P C K | Done | 2025-01-09 08:00 | 2025-10-09 18:00 | 3.0417 | None | Jeeveetha P C K | 100 | 2025-10-09 18:00 | 3.0417 | None
POSH Agreement - India | HR Team | Dimple Latha, Jeeveetha P C K | Open | 2025-01-09 08:00 | 2025-05-09 18:00 | 1.9167 | High | Jeeveetha P C K | 45 |  | 3.8333 | None
Screening calls for Technical Lead profiles from Naukri | HR Team | Jeeveetha P C K | Open | 2025-01-09 08:00 | 15-09-2025 06:00 PM | 4.1667 | None | Jeeveetha P C K | 80 |  | 4.1667 | None
Survey Results & Action Plans | HR Team | Yong Ching Fan | Open | 2025-01-09 08:00 | 23-09-2025 06:00 PM | 6.4167 | High | Yong Ching Fan | 20 |  | 6.4167 | None
Moving Values - Story 1 | HR Team | Yong Ching Fan | Open | 2025-01-09 08:00 | 30-09-2025 06:00 PM | 8.2917 | None | Yong Ching Fan | 60 |  | 8.2917 | None
Cross Functional Learning video editing - Townhall | HR Team | Yong Ching Fan | Open | 2025-09-09 08:00 | 2025-09-09 18:00 | 0.41667 | High | Yong Ching Fan | 45 |  | 0.41667 | None
Joshua 's Relocation Documentation | HR Team | Yong Ching Fan | Open | 2025-01-09 08:00 | 31-10-2025 06:00 PM | 16.9167 | Medium | Yong Ching Fan | 50 |  | 16.9167 | None
Dubai Hiring - Sales Executive | HR Team | Yong Ching Fan | Open | 2025-10-09 08:00 | 30-09-2025 06:00 PM | 5.6667 | Medium | Yong Ching Fan | 80 |  | 5.6667 | None
Advaita's Job Application - Sri request | HR Team | Yong Ching Fan | Open | 2025-10-09 08:00 | 18-09-2025 06:00 PM | 2.6667 | Medium | Yong Ching Fan | 20 |  | 2.6667 | None
Hiring ambassador | HR Team | Jayasri Sridhar | Open | 2025-01-10 08:00 | 15-10-2025 06:00 PM | 4.1667 | None | Jayasri Sridhar | 60 |  | 4.1667 | None
Hiring Head of Business - SG (Rajan Batra) | HR Team | Muhamad Hasif Daud, Yong Ching Fan | Open | 18-09-2025 08:00 AM | 2025-01-10 18:00 | 3.7917 | High | Yong Ching Fan | 45 |  | 7.5833 | None
Trainee Hiring - SG (close - no decision made) | HR Team | Yong Ching Fan | Open | 18-09-2025 08:00 AM | 30-09-2025 06:00 PM | 3.4167 | Medium | Yong Ching Fan | 50 |  | 3.4167 | None
Payroll Processing | HR Team | Muhamad Hasif Daud | Open | 22-09-2025 08:00 AM | 30-09-2025 06:00 PM | 2.6667 | High | Muhamad Hasif Daud | 55 |  | 2.6667 | None
Agreements & Letters | HR Team | Muhamad Hasif Daud | Open | 22-09-2025 08:00 AM | 24-09-2025 06:00 PM | 1.1667 | High | Muhamad Hasif Daud | 68 |  | 1.1667 | None
Employment Pass - Interview Stage (Ashwini) | HR Team | Muhamad Hasif Daud | Done | 25-09-2025 08:00 AM | 30-09-2025 06:00 PM | 1.5417 | Medium | Muhamad Hasif Daud | 100 | 30-09-2025 06:00 PM | 1.5417 | None
Intern Timesheet | HR Team | Yong Ching Fan | Open | 26-09-2025 08:00 AM | 26-09-2025 06:00 PM | 0.41667 | Low | Yong Ching Fan | 45 |  | 0.41667 | None
EPF Registration - Expatriate | HR Team | Muhamad Hasif Daud | Open | 2025-03-10 08:00 | 31-10-2025 06:00 PM | 7.9167 | High | Muhamad Hasif Daud | 80 |  | 7.9167 | None
Payroll Summary - Finance | HR Team | Muhamad Hasif Daud | Open | 2025-09-10 08:00 | 2025-10-10 18:00 | 0.79167 | High | Muhamad Hasif Daud | 20 |  | 0.79167 | None
CMO | HR Team | Yong Ching Fan | Open | 16-10-2025 08:00 AM | 28-11-2025 06:00 PM | 12.0417 | None | Jayasri Sridhar | 60 |  | 12.0417 | None
CFO | HR Team | Jayasri Sridhar | Open | 16-10-2025 08:00 AM | 31-10-2025 06:00 PM | 4.5417 | None | Jayasri Sridhar | 80 |  | 4.5417 | None
Prachi Offer letter | HR Team | Jayasri Sridhar | Open | 16-10-2025 08:00 AM | 31-10-2025 06:00 PM | 4.5417 | Medium | Jayasri Sridhar | 20 |  | 4.5417 | None
Diya - Lead Product Marketing | HR Team | Jayasri Sridhar | Open | 16-10-2025 08:00 AM | 31-10-2025 06:00 PM | 4.5417 | None | Jayasri Sridhar | 60 |  | 4.5417 | None
Story Time | HR Team | Kushpu S, Yong Ching Fan | Open | 2025-01-10 08:00 | 15-10-2025 06:00 PM | 4.1667 | Medium | Jayasri Sridhar | 45 |  | 8.3333 | None
Focus Group | HR Team | Kushpu S, Yong Ching Fan | Open | 2025-01-10 08:00 | 15-10-2025 06:00 PM | 4.1667 | None | Jayasri Sridhar | 50 |  | 8.3333 | None
Zoho WFH tab to be moved under attendance | HR Team | Meenakshi Dabral, Govind Anantharaman | Open | 2025-01-10 08:00 | 15-10-2025 06:00 PM | 4.1667 | High | Jayasri Sridhar | 55 |  | 8.3333 | None
Rajan & Ahmed Onboarding | HR Team | Yong Ching Fan | Open | 2025-01-10 08:00 | 17-10-2025 06:00 PM | 4.9167 | Medium | Yong Ching Fan | 68 |  | 4.9167 | None
Stories Deck for Townhall | HR Team | Yong Ching Fan | Done | 13-10-2025 08:00 AM | 14-10-2025 06:00 PM | 0.79167 | High | Yong Ching Fan | 100 | 14-10-2025 06:00 PM | 0.79167 | None
Salary Grid | HR Team | Muhamad Hasif Daud | Open | 13-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.6667 | High | Muhamad Hasif Daud | 80 |  | 5.6667 | None
Hiring - CMO & CFO | HR Team | Yong Ching Fan | Open | 2025-01-10 08:00 | 31-10-2025 06:00 PM | 8.6667 | High | Yong Ching Fan | 20 |  | 8.6667 | None
WFH Button Announcement | HR Team | Yong Ching Fan | Open | 13-10-2025 08:00 AM | 13-10-2025 06:00 PM | 0.41667 | High | Yong Ching Fan | 60 |  | 0.41667 | None
Enabling Geo Fencing Attendance for - Chennai, Blr & Mumbai offices | HR Team | Dimple Latha | Open | 2025-09-10 08:00 | 13-10-2025 06:00 PM | 1.1667 | None | Jeeveetha P C K | 45 |  | 1.1667 | None
Zoho WFH tab to be moved under Attendance | HR Team | Meenakshi Dabral, Govind Anantharaman | Open | 2025-01-10 08:00 | 15-10-2025 06:00 PM | 4.1667 | None | Jayasri Sridhar | 50 |  | 8.3333 | None
Post- training efficiency improvements of employees atleast for two function - Ask feedback from mgrs | HR Team | Kushpu S | Open | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 55 |  | 5.2917 | None
Band strcuture and roles - Role Mappping , JD Validation for role clarity with 15 values/competencies weightage clearly defined ( for all emplyees below Middle Managers) , self development? | HR Team | Kushpu S | Open | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 68 |  | 5.2917 | None
Hiring - Solution Architect (Contract) | HR Team | Kushpu S | Done | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 100 | 31-10-2025 06:00 PM | 5.2917 | None
Attrition data in Zoho: Publish Jan to Dec Exit employee dashboard and reasons - India Location | HR Team | Kushpu S | Open | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 45 |  | 5.2917 | None
Mid-Manager Capability Program (matrix) : Develop and roll out a mid-manager capability framework (including assessment + values alignment) AI assessment testing for all mid managers | HR Team | Kushpu S | Open | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 50 |  | 5.2917 | None
Organise Agility workshop to train all people managers to run weekly agile reviews | HR Team | Kushpu S | Open | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 55 |  | 5.2917 | None
Skill Gap - Complete the delivery of learning and track progress for Tech Function + AdTech (NM Team) | HR Team | Kushpu S | Open | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 68 |  | 5.2917 | None
Prepare HR Calendar - Training & Dev | HR Team | Kushpu S | Done | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 100 | 31-11-2025 06:00 PM | 5.2917 | None
Run VOE Session for all your functions and100% action plan completion from VOE captured. | HR Team | Kushpu S | Open | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 80 |  | 5.2917 | None
HR Week drive with activity and show case MW Value story to all India employees | HR Team | Kushpu S | Open | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 20 |  | 5.2917 | None
Excute Remote employee engagment plan for India, Srilanka & SA | HR Team | Kushpu S | Open | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | None | Kushpu S | 60 |  | 5.2917 | None
Ensure Q4 100% reviews completed within the set timeline | HR Team | Kushpu S | Open | 2025-06-11 08:00 | 28-11-2025 06:00 PM | 6.4167 | None | Kushpu S | 45 |  | 6.4167 | None
Insightz Club - Seating Arrangements | HR Team | Yong Ching Fan | Open | 14-10-2025 08:00 AM | 31-10-2025 06:00 PM | 5.2917 | High | Yong Ching Fan | 80 |  | 5.2917 | None
PD's Team Attendance (Oshin) | HR Team | Yong Ching Fan | Open | 15-10-2025 08:00 AM | 17-10-2025 06:00 PM | 1.1667 | High | Yong Ching Fan | 20 |  | 1.1667 | None
Vignesh Onboarding | HR Team | Kushpu S | Open | 16-10-2025 08:00 AM | 24-10-2025 06:00 PM | 2.6667 | None | Kushpu S | 60 |  | 2.6667 | None
Global HR Calendar | HR Team | Jeeveetha P C K, Yong Ching Fan | Open | 16-10-2025 08:00 AM | 31-10-2025 06:00 PM | 4.5417 | None | Dimple Latha | 45 |  | 9.0833 | None
Update MW Career Page | HR Team | Jayasri Sridhar | Open | 22-10-2025 08:00 AM | 31-10-2025 06:00 PM | 3.0417 | None | Jayasri Sridhar | 50 |  | 3.0417 | None
Story Time - Online (22/10) | HR Team | Yong Ching Fan | Open | 22-10-2025 08:00 AM | 22-10-2025 06:00 PM | 0.41667 | High | Yong Ching Fan | 55 |  | 0.41667 | None
Payroll Processing | HR Team | Muhamad Hasif Daud | Open | 21-10-2025 08:00 AM | 31-10-2025 06:00 PM | 3.4167 | High | Muhamad Hasif Daud | 68 |  | 3.4167 | None
NM's Dependent Pass renewal | HR Team | Muhamad Hasif Daud | Done | 16-10-2025 08:00 AM | 31-10-2025 06:00 PM | 4.5417 | High | Muhamad Hasif Daud | 100 | 31-10-2025 06:00 PM | 4.5417 | None
Deepavali Potluck KL office | HR Team | Yong Ching Fan | Open | 17-10-2025 08:00 AM | 24-10-2025 06:00 PM | 2.2917 | High | Yong Ching Fan | 45 |  | 2.2917 | None
PD's Team Attendance (Steffi) | HR Team | Yong Ching Fan | Open | 2025-06-10 08:00 | 24-10-2025 06:00 PM | 5.6667 | High | Yong Ching Fan | 50 |  | 5.6667 | None
Firechat Session in ASB Campus | HR Team | Yong Ching Fan | Open | 21-10-2025 08:00 AM | 14-11-2025 06:00 PM | 7.1667 | Medium | Yong Ching Fan | 20 |  | 7.1667 | None
CFO - Linkedin Post | HR Team | Yong Ching Fan | Open | 21-10-2025 08:00 AM | 23-10-2025 06:00 PM | 1.1667 | High | Yong Ching Fan | 60 |  | 1.1667 | None
Hiring - TL in Chennai | HR Team | Kushpu S | Open | 2025-06-11 08:00 | 28-11-2025 06:00 PM | 6.4167 | None | Kushpu S | 45 |  | 6.4167 | None
Full Stack Contract (4 positions) | HR Team | Jayasri Sridhar | Open | 28-10-2025 08:00 AM | 14-11-2025 06:00 PM | 5.2917 | None | Jayasri Sridhar | 80 |  | 5.2917 | None
Adtech Sales Manager | HR Team | Jayasri Sridhar, Yong Ching Fan | Open | 23-10-2025 08:00 AM | 28-11-2025 06:00 PM | 10.1667 | None | Jayasri Sridhar | 20 |  | 20.3333 | None
SA Support Engineer Replacement | HR Team | Jayasri Sridhar | Open | 28-10-2025 08:00 AM | 28-11-2025 06:00 PM | 9.0417 | None | Jayasri Sridhar | 60 |  | 9.0417 | None
CFO Position | HR Team | Yong Ching Fan | Open | 27-10-2025 08:00 AM | 31-10-2025 06:00 PM | 1.9167 | High | Yong Ching Fan | 45 |  | 1.9167 | None
Who am I? initiative | HR Team | Yong Ching Fan | Open | 29-10-2025 08:00 AM | 14-11-2025 06:00 PM | 4.9167 | Low | Yong Ching Fan | 50 |  | 4.9167 | None
Implementation of AI Policy | HR Team | Jeeveetha P C K | In Progress | 24-10-2025 09:00 AM | 31-10-2025 06:00 PM | 6 | High | Jeeveetha P C K | 80 |  | 2.25 | None
Promote company brand on job boards and LinkedIn | HR Team | Jayasri Sridhar | Open | 31-10-2025 09:00 AM | 14-11-2025 06:00 PM | 11 | None | Jayasri Sridhar | 20 |  | 4.125 | None
R& R Revamp Level 1 discussion with Task force | HR Team | Jeeveetha P C K | Open | 2025-04-11 09:00 | 15-11-2025 06:00 PM | 10 | High | Jeeveetha P C K | 60 |  | 3.75 | None
Bank Statement on Zoho | HR Team | Jeeveetha P C K | Open | 2025-01-11 09:00 | 15-11-2025 06:00 PM | 12 | None | Jeeveetha P C K | 45 |  | 4.5 | None
WFH Tracking In Zoho | HR Team | Jeeveetha P C K | Open | 2025-01-11 09:00 | 15-11-2025 06:00 PM | 12 | None | Jeeveetha P C K | 50 |  | 4.5 | None
Immigration - Dependent Pass (NM's Wife) - First Approval Stage | HR Team | Muhamad Hasif Daud | Open | 2025-03-11 08:00 | 14-11-2025 06:00 PM | 3.7917 | Medium | Muhamad Hasif Daud | 55 |  | 3.7917 | None
Pre-onboarding (Insightz Club) - Offer Letter, Email ID Creation, Payroll Summary, ZOHO account, Seat Arrangement, | HR Team | Muhamad Hasif Daud | Open | 2025-01-11 08:00 | 2025-10-11 18:00 | 2.6667 | High | Muhamad Hasif Daud | 68 |  | 2.6667 | None
Payroll - Global Cost Summary (Finance Team) | HR Team | Muhamad Hasif Daud | Done | 2025-01-11 08:00 | 2025-10-11 18:00 | 2.6667 | High | Muhamad Hasif Daud | 100 | 2025-10-11 18:00 | 2.6667 | None
Global Holiday Calendar - 2026 | HR Team | Muhamad Hasif Daud | Open | 2025-01-11 08:00 | 14-11-2025 06:00 PM | 4.1667 | Low | Muhamad Hasif Daud | 45 |  | 4.1667 | None
Nov Townhall HR Slides | HR Team | Jeeveetha P C K | Open | 2025-04-11 08:00 | 14-11-2025 06:00 PM | 3.4167 | None | Jeeveetha P C K | 50 |  | 3.4167 | None
PF - India (October) | HR Team | Jeeveetha P C K | Open | 2025-03-11 08:00 | 2025-04-11 18:00 | 0.79167 | High | Jeeveetha P C K | 20 |  | 0.79167 | None
Salary categorization for March & April for India Employee | HR Team | Jeeveetha P C K | Open | 2025-03-11 08:00 | 14-11-2025 06:00 PM | 3.7917 | None | Jeeveetha P C K | 60 |  | 3.7917 | None
Rekhassari's Contract Renewal | HR Team | Yong Ching Fan | Open | 2025-04-11 08:00 | 2025-07-11 18:00 | 1.5417 | High | Yong Ching Fan | 45 |  | 1.5417 | None
2026 KRAs - Insightz Club | HR Team | Yong Ching Fan | Open | 2025-04-11 08:00 | 28-11-2025 06:00 PM | 7.1667 | Low | Yong Ching Fan | 80 |  | 7.1667 | None
100% compliance on offers with complete documentation as per the checklist | HR Team | Jayasri Sridhar | Open | 2025-06-11 08:00 | 28-11-2025 06:00 PM | 6.4167 | None | Jayasri Sridhar | 20 |  | 6.4167 | None
Data Update - KRA & Goals for Q4 | HR Team | Kushpu S | Open | 2025-06-11 08:00 | 14-11-2025 06:00 PM | 2.6667 | None | Kushpu S | 45 |  | 2.6667 | None
Story Time (Remote staff) - 6th Nov | HR Team | Yong Ching Fan | Open | 2025-06-11 08:00 | 2025-06-11 18:00 | 0.41667 | Medium | Yong Ching Fan | 80 |  | 0.41667 | None

## Sheet2
Duration | Work hours
1 | 0.375
6.0417 | 6.0417
7.9167 | 15.8333
7.1667 | 7.1667
11.6667 | 11.6667
4.1667 | 4.1667
7.9167 | 7.9167
11.6667 | 11.6667
6.4167 | 6.4167
3.7917 | 3.7917
3.7917 | 3.7917
37 | 27.75
23 | 8.625
37 | 13.875
8.2917 | 8.2917
4.1667 | 12.5
3 | 2.25
9.7917 | 39.1667
1.9167 | 1.9167
5.6667 | 17
1.9167 | 1.9167
4.1667 | 4.1667
18.7917 | 37.5833
10.5417 | 21.0833
4.1667 | 4.1667
1.1667 | 1.1667
10.5417 | 10.5417
4.9167 | 4.9167
3.7917 | 3.7917
19.9167 | 19.9167
5.6667 | 5.6667
6.4167 | 12.8333
4.1667 | 4.1667
1.9167 | 1.9167
1.5417 | 1.5417
4.1667 | 4.1667
0.79167 | 0.79167
6.4167 | 6.4167
1.1667 | 1.1667
1.9167 | 9.5833
0.79167 | 0.79167
0.79167 | 0.79167
4.9167 | 4.9167
4.9167 | 4.9167
0.54167 | 1.0833
8.2917 | 8.2917
4.5417 | 9.0833
1.5417 | 1.5417
1.1667 | 1.1667
1.5417 | 1.5417
1.1667 | 2.3333
0.41667 | 0.41667
1.5417 | 3.0833
0.41667 | 0.41667
9.7917 | 9.7917
4.5417 | 4.5417
2.6667 | 2.6667
2.6667 | 2.6667
2.6667 | 2.6667
2.2917 | 2.2917
4.1667 | 8.3333
1.9167 | 1.9167
4.5417 | 4.5417
3.7917 | 3.7917
1.9167 | 1.9167
1 | 0.375
0.41667 | 0.41667
1.5417 | 1.5417
5.6667 | 5.6667
1.1667 | 1.1667
3.7917 | 3.7917
4.1667 | 8.3333
0.41667 | 1.25
1.5417 | 1.5417
3.0417 | 3.0417
1.5417 | 4.625
4.1667 | 4.1667
0.79167 | 0.79167
1.1667 | 2.3333
4.1667 | 4.1667
5.6667 | 5.6667
4.1667 | 4.1667
4.1667 | 8.3333
4.1667 | 4.1667
4.5417 | 9.0833
3.0417 | 9.125
1.9167 | 5.75
8.6667 | 8.6667
4.5417 | 4.5417
4.1667 | 12.5
2.2917 | 4.5833
0.41667 | 0.41667
2.6667 | 8
4.1667 | 4.1667
4.1667 | 4.1667
10.9167 | 10.9167
1.1667 | 1.1667
12.4167 | 12.4167
4.1667 | 4.1667
4.5417 | 4.5417
3.4167 | 3.4167
23.2917 | 23.2917
0.41667 | 0.41667
1.5417 | 1.5417
2.6667 | 2.6667
2.2917 | 2.2917
1 | 0.75
1.9167 | 1.9167
0.79167 | 0.79167
3.7917 | 7.5833
3.0417 | 3.0417
4.5417 | 4.5417
4.5417 | 9.0833
4.1667 | 4.1667
3.0417 | 3.0417
0.41667 | 0.41667
0.41667 | 0.41667
4.1667 | 4.1667
4.1667 | 4.1667
1.1667 | 1.1667
1.9167 | 3.8333
3.4167 | 3.4167
1.1667 | 1.1667
1.1667 | 1.1667
27.4167 | 27.4167
4.1667 | 4.1667
0.79167 | 0.79167
1.1667 | 1.1667
4.1667 | 4.1667
4.1667 | 4.1667
1.5417 | 1.5417
3.4167 | 3.4167
1.9167 | 1.9167
0.41667 | 0.41667
7.9167 | 7.9167
4.1667 | 4.1667
1.1667 | 1.1667
3.7917 | 3.7917
3.7917 | 3.7917
16.1667 | 16.1667
4.5417 | 9.0833
4.1667 | 4.1667
2.2917 | 2.2917
6.7917 | 6.7917
8.2917 | 16.5833
4.1667 | 12.5
8.2917 | 16.5833
4.5417 | 4.5417
6.7917 | 6.7917
6.4167 | 6.4167
1.9167 | 1.9167
3.7917 | 3.7917
2.2917 | 2.2917
0.79167 | 0.79167
1.9167 | 1.9167
3.7917 | 3.7917
2.2917 | 2.2917
1.9167 | 1.9167
7.5417 | 7.5417
1.9167 | 1.9167
0.41667 | 0.41667
3.4167 | 3.4167
2.6667 | 2.6667
2.6667 | 2.6667
3.0417 | 3.0417
16.5417 | 16.5417
4.5417 | 4.5417
1.9167 | 1.9167
1.1667 | 1.1667
3.4167 | 3.4167
1.5417 | 1.5417
3.0417 | 3.0417
1.9167 | 3.8333
4.1667 | 4.1667
6.4167 | 6.4167
8.2917 | 8.2917
0.41667 | 0.41667
16.9167 | 16.9167
5.6667 | 5.6667
2.6667 | 2.6667
4.1667 | 4.1667
3.7917 | 7.5833
3.4167 | 3.4167
2.6667 | 2.6667
1.1667 | 1.1667
1.5417 | 1.5417
0.41667 | 0.41667
7.9167 | 7.9167
0.79167 | 0.79167
12.0417 | 12.0417
4.5417 | 4.5417
4.5417 | 4.5417
4.5417 | 4.5417
4.1667 | 8.3333
4.1667 | 8.3333
4.1667 | 8.3333
4.9167 | 4.9167
0.79167 | 0.79167
5.6667 | 5.6667
8.6667 | 8.6667
0.41667 | 0.41667
1.1667 | 1.1667
4.1667 | 8.3333
5.2917 | 5.2917
5.2917 | 5.2917
5.2917 | 5.2917
5.2917 | 5.2917
5.2917 | 5.2917
5.2917 | 5.2917
5.2917 | 5.2917
5.2917 | 5.2917
5.2917 | 5.2917
5.2917 | 5.2917
5.2917 | 5.2917
6.4167 | 6.4167
5.2917 | 5.2917
1.1667 | 1.1667
2.6667 | 2.6667
4.5417 | 9.0833
3.0417 | 3.0417
0.41667 | 0.41667
3.4167 | 3.4167
4.5417 | 4.5417
2.2917 | 2.2917
5.6667 | 5.6667
7.1667 | 7.1667
1.1667 | 1.1667
6.4167 | 6.4167
5.2917 | 5.2917
10.1667 | 20.3333
9.0417 | 9.0417
1.9167 | 1.9167
4.9167 | 4.9167
6 | 2.25
11 | 4.125
10 | 3.75
12 | 4.5
12 | 4.5
3.7917 | 3.7917
2.6667 | 2.6667
2.6667 | 2.6667
4.1667 | 4.1667
3.4167 | 3.4167
0.79167 | 0.79167
3.7917 | 3.7917
1.5417 | 1.5417
7.1667 | 7.1667
6.4167 | 6.4167
2.6667 | 2.6667
0.41667 | 0.41667